## Matrix
RACI Matrix
HR Payroll automation | [7 empty] | RACI Matrix Template
© 2018 Vertex42.com
|  | ROLES | Mohammed (Consultant) | Tshepiso (Consultant) | Premal (Consultant) | Chris Lucas (Senior Consultant) | Jenny (HR manager) | ◄ Insert more roles by inserting new columns
| Deliverable or Task | Status | Project Team |  |  | QA Liason | Company Liason | ◄ Edit role categories to aid in organization
Planning
| Create flow: Processing Consultant invoices |  | R | I | I | A | C | Edit color-coding via Home > Conditional Formatting
| Create flow: Collate hours worked from employees and send reports |  | I | R | I | A | C
| Create flow: Manually making and sending payslips to all employees |  | I | I | R | A | C
| BOSCARD |  | I | R | I | A | C
| RACI |  | I | I | R | A | C
| DPD |  | R | R | R | A | C
| Process Assessment |  | R | R | R | A | C
| Project overview |  | R | R | R | A | C
| Risk assessment |  | R | I | I | A | C
| ERD |  | I | I | R | A | C
| Execution | [6 empty] | To clear the sample set of data, select cells and press Delete
| Create process: Processing Consultant invoices |  | I | I | I | A | C
| Create process: Collate hours worked from employees and send reports |  | I | I | I | A | C
| Create process: Manually making and sending payslips to all employees |  | I | I | I | A | C
| Orchestrator |  | C | C | C | A | I
| Testing |  | R | R | R | A | I
Deployment
| Integrate with HR Database |  |  |  |  | A | I
Deploy automation
D | Driver | Assists those who are responsible for a task. | [5 empty] | ◄ Delete unneeded rows to remove from the drop-down lists
R | Responsible | Assigned to complete the task or deliverable. | [5 empty] | ◄ Edit the table of abbreviations and definitions as needed
A | Accountable | Has final decision-making authority and accountability for completion. Only 1 per task.
S | Support | Provides support during implementation.
C | Consulted | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action.
I | Informed | Must be informed after a decision or action.

## About
RACI MATRIX TEMPLATE by Vertex42.com
https://www.vertex42.com/ExcelTemplates/raci-matrix.html
© 2018 Vertex42 LLC
About This Template
Use this template within your project team to help clarify and communicate roles and responsibilities for each task or deliverable. Start by inserting rows to define the tasks and deliverables and insert columns as needed to define the roles of sponsors, leaders, consultants, and project team members. Customize the abbreviations below the chart based on the method you are using (RACI, DRASCI, CAIRO, etc.).
Terms of Use / Copyright
This template is a copyrighted work. Do not submit copies or modifications of this template to any website or online template gallery. Click on the link below to learn how you may or may not use this template.
License: Private Use Only
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.