## Sheet1
Risk | Effect | Response Strategy | Baseline
|  |  | Likelihood | Severity | Risk Level (S x L)
Selecting poor use-case to automate | Selecting a poor candidate to automate can lead to a halted project, whereby many issues occur due to the variability, scope, 3rd party systems.. | Complete Process Assessment, ensure that the processes being automate fit the criteria for RPA. | 5 | 5 | 25
No Objective | Can lead to misdirection of project, leaving goals unfulfilled. | Ensure planning is comprehensive, creating an overview, BOSCARD. Keeping track of the scope of project. | 4 | 5 | 20
Miss Deadline | End with a incomplete project, whereby targets were not met. | Careful planning, with deadlines set for each task. Create an MVP to have an idea what an acceptable end product will look like. | 3 | 5 | 15
Outlook Spam Filter | Trouble with email, prohibits to test email | Use different mail provider, send email to outbox or drafts. | 5 | 3 | 15
Combining individual work together | As each member works on individual tasks, can end up with silos. | Make sure we leave enough time to combine workflows. Also make use of flowchart tools. | 3 | 5 | 15
Lack of communication | Poor communication with team can lead to misunderstandings, leading to many errors. | Daily stand-up to ensure everybody is on the same page. Set up Trello board, shared folder to track each others progress. | 2 | 5 | 10
System issues | Network/Hardware/Software issues (internet connection, file errors) | Can use mobile as hotspot if available, also alert trainer and team members as soon as possible. Ensure files are pushed to github, so no files are lost and updates are not lost. | 2 | 4 | 8
Lack of knowledge | Can cause delays in progression, lose sight of overall objectives, missing other deadlines on other tasks. | Use UiPath forums to navigate around any issues, also can use the trainer if unable to find suitable solution using resources online. | 3 | 2 | 6